ANNEX II: TERMS OF REFERENCE

1.	BACKGROUND INFORMATION	2

1.1.	Partner country	2

1.2.	Contracting authority	2

1.3.	Country background	2

1.4.	Current situation in the sector	2

1.5.	Related programmes and other donor activities	2

2.	OBJECTIVES & EXPECTED OUTPUTS	2

2.1.	Overall objective	3

2.2.	Specific objective(s)	3

2.3.	Expected outputs to be achieved by the contractor	3

3.	ASSUMPTIONS & RISKS	4

3.1.	Assumptions underlying the project	4

3.2.	Risks	4

4.	SCOPE OF THE WORK	4

4.1.	General	4

4.2.	Specific work	4

4.3.	Project management	5

5.	LOGISTICS AND TIMING	5

5.1.	Location	5

5.2.	Start date & period of implementation of tasks	5

6.	REQUIREMENTS	5

6.1.	Personnel	5

6.2.	Office accommodation	6

6.3.	Facilities to be provided by the contractor	6

6.4.	Equipment	7

7.	REPORTS	7

7.1.	Reporting requirements	7

7.2.	Submission and approval of reports	7

8.	MONITORING AND EVALUATION	8

8.1.	Definition of indicators	8

8.2.	Special requirements	8

# BACKGROUND INFORMATION

## Partner country

Republic of North Macedonia

## Contracting authority

Balkan Foundation for Sustainable Development (BFSD)

Republic of North Macedonia is a country in Southeast Europe. It gained independence in 1991 as one of the successor states of Yugoslavia. North Macedonia is a landlocked with total area of 25,713 km2. It lies between latitudes 40° and 43° N, and mostly between longitudes 20° and 23° E (a small area lies east of 23°). North Macedonia has some 748 km of boundaries, shared with Serbia (62 km) to the north, Kosovo (159) to the northwest, Bulgaria (148 km) to the east, Greece (228 km) to the south, and Albania (151 km) to the west. It constitutes approximately the northern third of the larger geographical region of Macedonia. Skopje, the capital and largest city, is home to a quarter of the country's 2.08 million population. The majority of the residents are ethnic Macedonians, a South Slavic people. Albanians form a significant minority at around 25%, followed by Turks, Romani, Serbs, Bosniaks, and Aromanians.

The Project Wild-A will be implemented in the cross-border area between North Macedonia and Greece, in accordance with the Interreg VI-A IPA Programme “Greece – Republic of North Macedonia 2021-2027”.

Activities in the assignments which are described in these Terms of References, should reflect target area of Wild-A project.

## Related programmes and other donor activities

Not applicable

# OBJECTIVES & EXPECTED OUTPUTS

The project addresses the urgent need for wildfire prevention and biodiversity protection in two high-risk cross border areas: the suburban pine forest of Edessa, Greece and the JASEN multipurpose natural area in North Macedonia. Both regions face escalating threats from wildfires, endangering valuable ecosystems, urban infrastructure and water resources. The project will establish cutting-edge systems for early fire detection, automatic warnings and fire extinguishing. These measures will safeguard the natural environment and he nearby urban zones.

## Overall objective

The overall objective of this assignment is to ensure the efficient, transparent, and compliant management of the Wild-A Project, supporting cross-border cooperation between Greece and North Macedonia in wildfire prevention, early detection, and biodiversity protection. The Contractor will be responsible for coordinating all administrative, technical, and financial management processes to guarantee that the project is implemented in accordance with the Interreg Greece–North Macedonia 2021–2027 Programme requirements and EU regulations.

## Specific objective(s)

The specific objective of this contract is to support BFSD in raising awareness and exchange of good practices on wildfire protection and sustainable forest management practices. .

In particular, the contract aims to:

- Reproduction of the brochures and roll-ups baners of the project & Ten high quality original photos by a professional photographer.

Need of the action: Dissemination of the project achievement.

Beneficiary’s outputs: Three versions of the brochure X 500 pieces each, 2 roller up banners, 10 high quality photos.

- Organization of Info days for the local stakeholders/communities: 2 in Skopje

Need of the action: Raising awareness and exchange of good practices for forest management

Beneficiary’s outputs: Increased awareness on good practices for forest management and silviculture

## Expected outputs to be achieved by the contractor

The service will be paid on the basis of the delivery of the specified output(s). Payments might be totally or partially withheld if the contractual result(s) have not been reached in conformity with the detailed terms of reference. Payment(s) is/are based on the approval of this/these deliverable(s). Partial payment has to be determined according to the partial implementation of the output(s).

The expected outputs of this contract are as follows:

Output 2.2 – Communication and Dissemination Materials

Three versions of the brochure in three languages (4 pages, full colour, A5) X 500 pieces each

Two roller up banners

Ten high-quality photos

Output 6.2 – Events organization

Two info days organized (agenda, invitation, venue, material, catering, etc).

# ASSUMPTIONS & RISKS

## Assumptions underlying the project

- Effective cooperation between BFSD, the Lead Beneficiary, and other Project Partners for joint communication activities.

- Continued institutional support from project partners and local stakeholders

- Availability of Programme guidance and timely feedback from the Programme Officer.

- Availability and continuous access to relevant information and access to project activities, project content, events and results suitable for dissemination.

- Stable operational conditions allowing continuous media and dissemination activities over the project period.

## Risks

- Delays in content validation or approvals of communication materials;

- Limited engagement of media or stakeholders at local level;

- Lower-than-expected social media engagement

- Overlapping or inconsistent messaging

- External factors affecting dissemination activities (e.g. public health or political constraints).

- External constraints affecting events

# SCOPE OF THE WORK

## General

The Wild-A Project addresses the urgent need for wildfire prevention and biodiversity protection in two high-risk cross-border areas: the suburban pine forest of Edessa, Greece, and the JASEN multipurpose natural area in North Macedonia. Both regions face increasing threats from wildfires, which endanger valuable ecosystems, biodiversity, urban infrastructure, and water resources.

To address these challenges, the project will establish innovative systems for early fire detection, automatic warning mechanisms, and fire extinguishing solutions. Through these interventions, the project aims to strengthen environmental protection, improve resilience to natural hazards, and safeguard nearby urban communities.

Within this framework, the Beneficiary requires external support for the implementation of communication, dissemination, and awareness-raising activities aimed at promoting project objectives, results, and good practices in wildfire prevention and sustainable forest management.

### 4.2 Description of the assignment

The overall objective of this assignment is to support the effective implementation of the Wild-A Project through the delivery of communication and dissemination activities, as well as the organization of awareness-raising events targeting local stakeholders and communities.

The specific objective is to assist BFSD in increasing public awareness of wildfire protection, biodiversity conservation, and sustainable forest management practices, while facilitating the exchange of knowledge and good practices among relevant stakeholders.

### Scope of Services

The Contractor shall be responsible for planning, coordinating, and implementing the following activities:

Task 1: Production of Communication and Dissemination Materials

The Contractor shall reproduce and deliver project communication materials in accordance with the visual identity requirements of the Interreg Greece–North Macedonia Programme and the project communication guidelines.

The Contractor shall: Design adaptation, proofreading, printing, and delivery of three language versions of the project brochure; Produce and deliver two roll-up banners for use during project events and dissemination activities; Organize a professional photography session and provide ten high-quality original photographs documenting project activities, events, and project-relevant locations; Ensure that all materials comply with EU visibility and communication requirements.

Task 2: Organization of Information Days

The Contractor shall organize two information days in Skopje aimed at local stakeholders, public institutions, forestry professionals, environmental organizations, local communities, and other relevant target groups.

The Contractor shall be responsible for: Preparing the event concept and agenda; Coordinating invitations and participant registration; Securing an appropriate venue and technical equipment; Providing event materials and participant packages; Organizing catering and logistical arrangements; Supporting presentations, discussions, and networking activities; Preparing event documentation, including participant lists, photographs, and event reports.

The information days shall focus on: Wildfire prevention and protection measures; Sustainable forest management practices; Biodiversity conservation; Exchange of experiences and good practices between stakeholders.

### Geographical area to be covered

The assignment covers the cross-border area of the Republic of North Macedonia.

### Target groups

- Local and regional authorities and institutions;

- Stakeholders and communities;

- Media representatives;

- General public and visitors to the cross-border area.

## Project management

### 4.3.1. Responsible body

The Contracting Authority is BFSD acting as responsible partner for Deliverables D2.2 and D6.2. The day-to-day operational project implementation will be performed by BFSD’s project office – which is responsible for implementation of project.

4.3.2. Management structure

A designated Project Manager within BFSD shall be responsible for the overall coordination, supervision, and monitoring of the contract. The Project Manager shall serve as the primary contact point for the contractor and shall ensure alignment of all activities with the Wild-A project objectives, approved work plan, and communication strategy.

4.3.3. Facilities

The Contracting Authority will provide all available information and will fully co-operate with the Contractor in order to achieve the best results. Technical information and access to the project documentation, branding guidelines existing records, any useful information and/or documentation which may be relevant to the performance of the Contract will be provided upon request.

# LOGISTICS AND TIMING

## Location

The services shall be implemented primarily in the Cross Border Area of Republic of North Macedonia with Greece.

## Start date & period of implementation of tasks

The intended start date is to be specified in the contract approximately beginning of July 2026. The period of implementation shall be aligned with the Wild-A project timeline i.e 3 months from signing of contract.

# REQUIREMENTS

## Personnel

Note that civil servants and other staff of the public administration of the partner country, or of international/regional organisations based in the country, shall only be able to provide input as experts if well justified. The justification should be submitted with the tender and shall include information on the added value the expert will bring as well on any potential interference or conflict of interest of the proposed expert in his/her function as expert and his/her present or previous functions working as civil servant. Moreover proof should be submitted that the expert is seconded or on personal leave.

The selection procedures used by the contractor to select the experts who provide input to the contract must be transparent, must guarantee the absence of professional conflicting interests and the absence of any discrimination based on former or current nationality, gender, place of residence, or any other ground. The findings of the selection panel must be recorded.

All experts must be independent and free from conflicts of interest in the responsibilities they take on.

### Experts

Minimum requirements for experts are not defined.

### Support facilities & backstopping

The costs for support facilities, including backstopping, are included in the tenderer's financial offer.

## Office accommodation

Office accommodation for each expert providing input to the contract is to be provided by the contractor.

## Facilities to be provided by the contractor

The contractor shall ensure that experts are adequately supported and equipped. In particular it must ensure that there is sufficient administrative, secretarial and interpreting provision to enable experts to concentrate on their primary responsibilities. It must also transfer funds as necessary to support their work under the contract and to ensure that its employees are paid regularly and in a timely fashion.

## Equipment

No equipment is to be purchased on behalf of the contracting authority / partner country as part of this service contract or transferred to the contracting authority / partner country at the end of this contract. Any equipment related to this contract which is to be acquired by the partner country must be purchased by means of a separate supply tender procedure.

# REPORTS

## Reporting requirements

The contractor will submit the following reports in English in one original:

- Progress Report of maximum 3 pages (main text, excluding annexes) to be produced after 1 months from the start of implementation. In the report the contractor shall describe progress of the implementation of the tasks.

## Submission and approval of reports

The report referred to above must be submitted to the project manager identified in the contract. The project manager is responsible for approving the reports.

# MONITORING AND EVALUATION

## Definition of indicators

Monitoring shall be based on quantitative indicators, directly linked to WP2 D2.2 and D6.2 outputs.

## Special requirements

N/A